## IED
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN: INFRASTRUCTURE AND ECONOMIC DEVELOPMENT
PERSON RESPONSIBLE: GENERAL MANAGER INFRASTRUCTURE AND ECONOMIC DEVELOPMENT
SDBIP REF. | IDP REF. | National KPAs | Programme | Measurable Objective | Ward | Baseline/ Status Quo | Annual KPI | Annual Target | Annual Budget Information |  |  |  | Quarterly Performance Targets
[9 empty] | OPEX | CAPEX | REVENUE | Funding Source | Q1 | Q1 POE | Q2 | Q2 POE | Q3 | Q3 POE | Q4 | Q4 POE
[9 empty] | VOTE | VOTE | VOTE
IED 1 | LED 1 | Local Economic Development | Renewable Energy | Alternative energy support initiative to infomal traders | All | 180 | Number of Informal Traders Supplied with wondercookers | 250 | 70000 | N/A | N/A | Internal Funding | Registration of Cooperatives | Registration certificate | Procurement Process | Copy of Ugu SPU Order Number | 250 | Copy of Invoice & Beneficiary register | Monitoring and evaluation | MANCO Extract noting report
[10 empty] | 0 | 0 |  | 0 |  | 0 |  | 70000 |  | 0
IED 2 | LED 3 |  | Creative Industry | Film production equipment | Ray Nkonyeni Municipality - Ward 18 | New project | Number of film production initiative supported with basic equipment | 1 | 100000 | N/A | N/A | Internal Funding | Projects identified and selected | MANCO Extract noting the Project selection report and projects identified for assistance | Procurement Process | Copy of Ugu SPU Order Number | 1 | Copy of Invoices & beneficiary register | Monitoring and evaluation | MANCO Extract noting report
[10 empty] | 0 | 0 |  | 0 |  | 0 |  | 100000 |  | 0
IED 3 | LED 3 |  |  | Local Artists performed in local event | Umzumbe-Wards 4, 12 ,17 & 18; Ray Nkonyeni Wards 1, 31, 4 & 17; Umuziwabantu Wards 3, 5 & 8 | 10 | Number of Local Music Artists Participated in Local Events | 12 | 100000 | N/A | N/A | Internal Funding | Implementation Plan | Extract Of MANCO Noting Implimentation Plan | 4 | Copies of Contract | 4 | Copies of Contract | 4 | Copies of Cotract
[10 empty] | 0 | 0 |  | 0 |  | 40000 |  | 20000 |  | 35000
IED 4 | LED 4 |  | SMME & Cooperative Sector | Cooperative Training | Ray Nkonyeni-3, Umuziwabantu-3, Umdoni-2, Umzumbe-2 | 120 | Number of Cooperative Trained on business management skills | 10 | 10000 | N/A | N/A | Internal Funding | Stakeholder engagement and collaboration | Attendance register | Co-operatives identification and selection | List of selected co-operatives | 10 | Attendance registers and certificates | Monitoring and evaluation | MANCO Extract noting M&E report
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 10000 |  | N/A
IED 5 | LED 4 |  |  | Trading Infrastructure Support for Informal Traders | Umzumbe-Ward 15 | New project | Number of mobile trading shelters provided for banana informal traders | 13 | 250000 | N/A | N/A | Internal Funding | Concept Document and Implementation Plan | Implementaton Plan Report noted by MANCO | SCM Process | letter of award | 13 | Invoice and beneficiary register | Monitoring and evaluation | MANCO Extract noting M&E report
[10 empty] | 0 | 0 |  | 0 |  | 10000 |  | 240000 |  | 0
IED 6 | LED 4 |  |  | Basic plumbing skills NQF L4 | All | 40 | Number of people trained in basic plumbing skills | 20 | 300000 | N/A | N/A | Internal Funding | Identification and selection of institution | Confirmation Letter from Institution | Identification and selection of trainees | List of trainees | Commencement of training | Admission letter(s) and attendance registers | 40 | Certificates
[9 empty] | 0 | 0 | 0 |  | 0 |  | 10000 |  | 290000 |  | 0
IED 7 | LED 5 |  | Agriculture Rural Development & Land Reform Sector | Rural Medium Scale Farming Support | All LMs | 12 | Number Agricultural Garden Projects Supported with fencing and irrigation | 4 | 300000 | N/A | N/A | Internal Funding | Identification and selection of projects Report | Extract of MANCO noting List of projects | Procurement Process | Copy of Ugu SPU Order Number | 4 | Copy of Invoice and beneficiary register | Monitoring and evaluation | MANCO Extract noting M&E report
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 100000 |  | 0
IED 8 | LED 5 |  |  | Tea Tree Essential Oils Project | Ezinqoleni | 7000 | Number Litres of Tea Tree Essential Oils Produced | 3000 | 0 | N/A | N/A |  | Distillery monitoring | Report noted by manco | Distillery monitoring | Report noted by manco | Distillery monitoring | Report noted by manco | 3000 | Production Records from Oribi Flats Farmers Association
[10 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 9 | LED 5 |  |  | Ugu Fresh Produce Market | Ray Nkonyeni Municipality Ward-21 | Existing | Date Ugu Fresh Produce Market Outsourced | 2017-06-30 | 10000 | N/A | N/A | Internal Funding | N/A | N/A | N/A | N/A | SCM Processes | Letter of Award | 2017-06-30 | Copy of Lease Agreement
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 10000 |  | N/A
IED 10 | LED 6 |  | Manufacturing Sector | Support for Emerging Manufactures | Ezinqoleni & Umuziwabantu | New | Number of Emerging Furniture Manufacturers provided with working material and equipment | 2 | 70000 | N/A | N/A |  | Projects identified and selected | MANCO Extract noting the Project selection report and projects identified for assistance | Procurement Process | Copy of Ugu SPU Order Number | 2 | Copy of Invoices & beneficiary register | Monitoring and evaluation | MANCO Extract noting report
[10 empty] | 0 | 0 |  | 0 |  | 0 |  | 70000 |  | 0
IED 11 | LED 6 |  |  |  | Vulamehlo & Umdoni | New | Number of Emerging Clothing Manufacturers provided with working material and equipment | 2 | 70000 | N/A | N/A |  | Projects identified and selected | MANCO Extract noting the Project selection report and projects identified for assistance | Procurement Process | Copy of Ugu SPU Order Number | 2 | Copy of Invoices & beneficiary register | Monitoring and evaluation | MANCO Extract noting report
[9 empty] | 0 | 0 | 0 |  | 0 |  | 70000 |  | 0 |  | 0
IED 12 | LED 6 |  |  |  | HCM & Umzumbe | New project | Number of Emerging Block Manufacturers provided with block making machine and water storage | 6 | 60000 | N/A | N/A | Internal Funding | Projects identified and selected | MANCO Extract noting the Project selection report and projects identified for assistance | Procurement Process | Copy of Ugu SPU Order Number | 2 | Copy of Invoices & beneficiary register | Monitoring and evaluation | MANCO Extract noting report
[10 empty] | 0 | 0 |  | 0 |  | 60000 |  | 0 |  | 100000
IED 13 | LED 8 |  | Employment Creation | Creation of job opportunities | All | 100 | Number of Job opportunities created through LED initiatives | 100 | 0 | N/A | N/A | Internal Funding | N/A | N/A | 40 | Extract of MANCO Noting job opportunities created | N/A | N/A | 100 | Extract of Munutes MANCO noting job opportunities created.
[10 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 14 | LED 9 |  | Research & Development | Economic Impact Study | All | 1 | Date Africa Bike Week Economic Impact Study Completed | 2017-06-30 | 40000 | N/A | N/A | Internal Funding | N/A | N/A | Concept Document & Implementation Plan | Extract of MANCO Noting the Concept Document & Implementation Plan | Field Work Completed | Field Woker List | 2017-06-30 | Extract of Minutes of MANCO Noting the Report
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 20000 |  | 20000
IED 15 | LED 9 |  |  | Sand Mining Development Program | All | New project | Date Sand Miners Needs Analysis Completed | 2017-06-30 | 30000 | N/A | N/A | Internal Funding | Concept and Implementation Plan | Extract from Manco noting the Implementation Plan | Stakeholder Consultation | Attendance Register | Field Work Completed | Field Woker List | 2017-06-30 | Extract of Minutes of MANCO Noting the Report
[10 empty] | 0 | 0 |  | 0 |  | 0 |  | 30000 |  | 0
IED 16 | LED 5 |  |  | Unemployed Graduates Database Project |  | All LM's | Date Unemployed Graduates Database Concept document completed | 2017-03-31 | 0 | N/A | N/A | External Funding | Database Close-out report | Extract from Manco noting report | N/A | N/A | 2017-03-31 | MANCO Extract noting Concept Document | N/A | N/A
[9 empty] | 40000 |  |  |  | 30000 |  | 0 |  | 10000 |  | 0
IED 17 | LED 5 |  |  | LED Capacity Support to LMs | ALL | 2 LM | Number of LED Interns placed in LMs | 4 | 168000 | N/A | N/A | Internal Funding | N/A | N/A | 4 | Contracts | N/A | N/A | N/A | N/A
[9 empty] | 0 | 0 | 0 |  | 7000 |  | 50000 |  | 50000 |  | 61000
IED 18 | LED 10 |  | Review of LED Sector Plans | LED Forum | All | New project | Number of LED Forum held | 4 | 10000 | N/A | N/A | Internal Funding | 1 | Minutes and Attendance Register | 2 | Minutes and Attendance Register | 3 | Minutes and Attendance Register | 4 | Minutes and Attendance Register
[10 empty] | 0 | 0 |  | 0 |  | 15000 |  | 15000 |  | N/A
IED 19 | LED 10 |  |  | LED Strategy Review | All | Existing | Date LED Strategy reviewed | 2017-06-30 | 400000 | N/A | N/A | N/A | Procurement Process Commenced | Tender Evaluation Report | Appointment of Service Provider | Letter of Appointment | Draft LED Strategy Document | Extract of Minutes from MANCO noting draft Strategy | 2017-06-30 | Extract of Minutes of Portfolio Noting the Strategy
[10 empty] | 0 | 0 |  | 10000 |  | 0 |  | 350000 |  | 40000
IED 20 | LED 10 |  |  | LED Road-Shows | All | New project | Number of LED Road-Shows Conducted | 2 | 10000 | N/A | N/A | Internal Funding | N/A | N/A | Road-Shows Implementation Plan | Extract of Minutes of Portfolio-Committee Noting the Implementation Plan | 1 | Attendance Register & Road-Show Report | 2 | Attendance Register & Road-Show Report
[10 empty] | 0 | 0 |  | 0 |  | 0 |  | 5000 |  | 5000
IED 21 | LED 12 |  | Tourism Development Program | South Coast Tourism Entity Activities | All | New project | Number of SC Tourism Entity Activities Monitored | 3 | 0 | N/A | N/A | N/A | N/A | N/A | 1 | Extract of Minutes of Portfolio-Committee Noting the Monitoring the Report | 2 | Extracts of Minutes of Port-folio Committee Noting the Monitoring Report | 3 | Extracts of Minutes of Port-folio Committee Noting the Monitoring Report
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED22 |  |  |  | South Coast Development Agency | All | New project | Number of SCDA Activities Monitored | 3 | 0 | N/A | N/A | N/A | N/A | N/A | 1 | Extract of Minutes of Portfolio-Committee Noting the Monitoring the Report | 3 | Extract of Minutes of Portfolio-Committee Noting the Monitoring the Report | 4 | Extract of Minutes of Portfolio-Committee Noting the Monitoring the Report
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 23 | LED 13 |  | Sports Development | Ug Sports and Leisure Centre | All | Existing | Number of USLC Maintenance Operations monitored | 4 | N/A | N/A | N/A | N/A | 1 | Maintenance Inspection Report noted by MANCO | 1 | Maintenance Inspection Report noted by MANCO | 1 | Maitenance Inspection Report noted by MANCO | 1 | Maintenance Inspection Report noted by MANCO
[9 empty] | 0 | 0 | 0
IED 24 | CCI 2 | CROSS-CUTTING INTERVENTIONS | Water Quality Monitoring | Water Sampling, testing & pollution | All | 1320 | Number of River Water Samples taken, and analysed | 400 | N/A | N/A | N/A | Internal Funding | 100 | laboratory reports | 100 | laboratory reports | 100 | laboratory reports | 100 | laboratory reports
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 25 | CCI 2 |  |  |  | All | New project | Number of WWTW / final effluent Water Samples taken, and analysed | 228 | N/A | N/A | N/A | Internal Funding | 57 | laboratory reports | 114 | laboratory reports | 171 | laboratory reports | 228 | laboratory reports
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 26 | CCI 2 |  |  |  | All | New project | Number of Standpipe Water Samples taken, and analysed | 240 | N/A | N/A | N/A | Internal Funding | 60 | laboratory reports | 120 | laboratory reports | 180 | laboratory reports | 240 | laboratory reports
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 27 | CCI 2 |  |  |  | All | New project | Number of Borehole Water Samples taken, and analysed | 100 | N/A | N/A | N/A | Internal Funding | 25 | laboratory reports | 50 | laboratory reports | 75 | laboratory reports | 100 | laboratory reports
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 28 | CCI 2 |  |  |  | All | New project | Number of Water tankers & water tanks/jojo tanks Samples taken, and analysed | 232 | N/A | N/A | N/A | N/A | 58 | laboratory reports | 116 | laboratory reports | 174 | laboratory reports | 232 | laboratory reports
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 29 | CCI 2 |  | Sanitation Monitoring | Sanitation contraventions | All | 100% | Percentage Investigations, monitoring & control of effluent discharges | 100% | 0 | 0 | 0 | N/A | 100% | monitoring reports noted by MANCO | 100% | monitoring reports noted by MANCO | 100% | monitoring reports noted by MANCO | 100% | monitoring reports noted by MANCO
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | 0 |  | 0
IED 30 | CCI 3 |  | Environmental Health Education | Public Health Education & Awareness Workshop | ALL | 820 | Number of Food Handlers /Event Caterers Awareness sessions held | 40 | 60000 | 0 | 0 | ES/Internal | 10 | report noted by MANCO/ Attendance registers | 20 | report noted by MANCO/ Attendance registers | 30 | report noted by MANCO/ Attendance registers | 40 | report noted by MANCO/ Attendance registers
[9 empty] | 320570 090-190 | N/A | N/A |  | 15000 |  | 30000 |  | 45000 |  | 60000
IED 31 | CCI 3 |  |  |  | ALL | 300 | Number of Communicable Disease Sessions Held | 300 | 25000 | 0 | 0 | ES/Internal | 75 | Report on Sessions Held noted by MANCO | 150 | Report on Sessions Held noted by MANCO | 225 | Report on Sessions Held noted by MANCO | 300 | Report on Sessions Held noted by MANCO
[9 empty] | 320570-090-190 | N/A | N/A |  | 6250 |  | 12500 |  | 18750 |  | 25000
IED 32 | CCI 3 |  |  |  | ALL | 120 | Number of Chemical Safety Sessions held | 120 | 25000 | 0 | 0 | ES/Internal | 30 | Report on Sessions Held noted by MANCO | 60 | Report on Sessions Held noted by MANCO | 90 | Report on Sessions Held noted by MANCO | 120 | Report on Sessions Held noted by MANCO
[9 empty] | 320570-090-190 | N/A | N/A |  | 6250 |  | 12500 |  | 18750 |  | 25000
IED 33 | CCI 3 |  |  |  | ALL | 60 | Number of PHAST Sessions Held | 60 | 25000 | 0 | 0 | Internal Funding | 15 | Report on Sessions Held noted by MANCO | 30 | Report on Sessions Held noted by MANCO | 45 | Report on Sessions Held noted by MANCO | 60 | Report on Sessions Held noted by MANCO
[9 empty] | 320570-090-190 | N/A | N/A |  | 6250 |  | 12500 |  | 18750 |  | 25000
IED 34 | CCI 3 |  |  |  | ALL | 300 | Number of Water & Sanitation | 300 | 25000 | 0 | 0 |  | 75 | Report on Sessions Held noted by MANCO | 150 | Report on Sessions Held noted by MANCO | 225 | Report on Sessions Held noted by MANCO | 300 | Report on Sessions Held noted by MANCO
[9 empty] | 320570-090-190 | N/A | N/A |  | 6250 |  | 12500 |  | 18750 |  | 25000
IED 35 | CCI 3 |  | Law Enforcement | Public Health By-Laws | N/A | Draft | Date by when Public Health By-laws gazzetted | 31 June 2017 | 110000 | 0 | 0 | Internal Funding | N/A | N/A | Public Participation | comments from public | By Laws submission to Council | Extract of Minutes of from Council Meeting | 31 June 2017 | Copy of Advert
[9 empty] | 321195-090-190 | N/A | N/A |  |  |  | 50000 |  | 0 |  | 110000
IED 36 | CCI 4 |  | Food Control | Swabbing/Microbial detection | All | 100 | Number of Microbial samples conducted | 100 | 60000 | 0 | 0 | Internal Funding | SCM processes | Copy of Tender Advert | Appointment of Service Provider | Appointment Letter | 50 | Sampling Reports | 100 | sampling reports
[9 empty] | 321552-090-190 | N/A | N/A |  | 0 |  | 0 |  | 33000 |  | 60000
IED 37 | CCI 4 |  |  | Inspections, actions/sessions | All | 700 | Number of Inspections and actions taken | 700 | 0 | 0 | 0 | N/A | 175 | Inspection reports, | 350 | Inspection reports, | 525 | Inspection reports, | 700 | Inspection reports,
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | 0 |  | 0
IED 38 | CCI 5 |  | Disposal of the Dead | Pauper burials | All | 100% | Percentage Qualifying paupers buried | 100 | 100000 | 0 | 0 | Internal funding | 100% | Invoice if requests received for pauper burial | 100% | Invoice if requests received for pauper burial | 100% | nvoice if requests received for pauper burial | 100% | Invoice if requests received for pauper burial
[9 empty] | 300171-010-020 | N/A | N/A |  | 35000 |  | 50000 |  | 75000 |  | 100000
IED 39 | CCI 6 | CROSS-CUTTING INTERVENTIONS | Premises surveillance | Building Plans | All | 100% | Percentage Building Plans scrutinised | 100 | 0 | 0 | 0 | N/A | 100% | Plans register per LM done, with an EH stamp. | 100% | Plans register per LM done, with an EH stamp. | 100% | Plans register per LM done, with an EH stamp. | 100% | Plans register per LM done, with an EH stamp.
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | 0 |  | 0
IED 40 | CCI 6 |  |  | Public and Private Facilities | All | 320 | Number of Inspections conducted for health compliance | 320 | 0 | 0 | 0 | N/A | 80 | Inspection report, | 160 | Inspection reports, | 240 | Inspection reports, | 320 | Inspection reports,
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | 0 |  | 0
IED 41 | CCI 7 |  | Communicable Disease Control | Communicable Disease Surveillance | All | 100% | Percentage Iinvestigation and reporting of Communicable Diseases investigated | 100 | 0 | 0 | 0 | N/A | 100% | Reports/notification | 100% | Reports/notification | 100% | Reports/notification | 100% | Reports/notification
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | 0 |  | 0
IED 42 |  |  | Waste Water Treatment Plant (WWTP) | Inspections. | All | 228 | Number of WWTPs 1Inspected | 268 | 0 | 0 | 0 | N/A | 67 | Inspection reports | 134 | Inspection reports | 201 | Inspection report | 268 | Inspection report
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | 0 |  | 0
IED 43 | CCI 8 |  | Air Quality Management Plan Implementation | Atmospheric Emissions Licencing - Issuing | All | 10 | Percentage AELs considered for decision as per applications received | 100 | R0,00 | R0,00 | R0,00 | N/A | 100% | Samples of copies of applications; Copies of AELs (if issued); Correspondences and info required | 100% | Samples of copies of applications; Copies of AELs (if issued); Correspondences and info required | 100% | Samples of copies of applications; Copies of AELs (if issued); Correspondences and info required | 100% | Samples of copies of applications; Copies of AELs (if issued); Correspondences and info required
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | 0 |  | 0
IED 44 | CCI 8 |  |  | Atmospheric Emissions Licences Monitoring | All | 9 Atmospheric Emmission licences issued | Number of Atmospheric Emmission licences monitored (maintained) | 10 | R0,00 | R0,00 | R0,00 | N/A | 10 | Correspondences with licencees | 10 | Correspondences with licencees | 10 | Correspondences with licencees | 10 | 1 Annual report on the state of compliance of all facilities
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | 0 |  | 0
IED 45 | CCI 8 |  |  | Faciliate Air Quality Management (AQM) forum workshops | All | None | Number of AQM forums workshops/year facilitated | 2 | 0 | 0 | 0 | N/A | n/a | n/a | 1 | Workshop minutes; agenda; Attendance register | N/A | N/A | 2 | Forum minutes; Attendance register, agenda
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | 0 |  | 0
IED 46 | CCI 8 |  |  | Co-Management agreement for sugarcane burning | All | None | Date Agreement between Ugu and a civic organisation | 2017-06-30 | R0,00 | R0,00 | R0,00 | N/A | Draft an MoU | Draft MoU | Workshop MoU between Ugu and CGA | Progress report on the MoU | n/a | n/a | 2017-06-30 | Signed MoU
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | R0,00 |  | 0
IED 47 | CCI 10 |  | Climate Change Response | Climate Change Desktop Vulnerability survey and Response Strategy | All | none | Date Draft Climate Change Vulnerability Survey and Response Strategy developed | 2016-12-30 | 110000 | 0 | R110, 000 | ES/Internal | Finalisation of Strategy | Draft Strategy | 2016-12-30 | Adopted Strategy and Council Resolution | Implementation plan | Implementation plan
[9 empty] | 320230-090-190-000-000-000 | N/A | N/A |  | 110000 |  | 0 |  | 0 |  | 0
IED 48 | CCI 11 |  | Integrated Environmental Management (IEM) | Implementation of Environmental Management Programme (EMPr) | N/A | EMPr Workshops; 16 projects/annum | Number of Projects/cases of compliance (non) | 16 | N/A | 0 | 0 | N/A | 4 | Compliance reports to MANCO, site meeting registers | 4 | Compliance reports to MANCO, site meeting registers | 4 | Compliance reports to MANCO, site meeting registers | 4 | Annual compliance report to MANCO
[10 empty] | N/A | N/A
IED 49 | CCI 11 |  |  | Biodiversity/Env Management Programme | N/A | None | Date Biodiversity/Env Management Programme developed | 30 June 2017 | R515,200 | N/A | N/A | ES/Internal | Terms of Reference | Terms of Reference | SCM processes | Proof of SCM processes | Appointment of service provider; Inception meeting | Record of Appointment; Inception report (minutes) | 2017-06-30 | Draft Biodiversity/Env. Management Programme
[9 empty] | 320475-090-190 | [5 empty] | R20,000 |  | 0 |  | 0
IED 50 | CCI 11 |  |  | Environmental protection and biodiversity management | Vulamehlo & Umzumbe | 1 pilot-Umzumbe & Vulamehlo LM | Number of Problem (bushpigs) animals management projects implemented | 2 | R300, 000 | 0 | 0 | ES/Internal | SCM processes | Proof of SCM processes | Appointment of service Provider; Inception | Appointment record; Inception report | 1 | Progress reports to MANCO | 2 | Progress reports to MANCO
[9 empty] | 320146-090-190 | N/A | N/A | [5 empty] | R150,000.00 |  | R150,000.00
IED 51 | CCI 11 |  |  | Pilot - Co-Management initiative with civic organisation for pollution management | Umdoni and HCM | None | Date pilot co-management initiative with 1 civic organisation | 2017-06-30 | R0,00 | N/A | N/A | MIG/WSO | 1 workshop with 1 conservancy | Workshop report to MANCO / minutes of the workshop | Draft a delivery plan / agreement | Draft a delivery plan / draft agreement | N/A | N/A | 2017-06-30 | Final plan/Agreement
[9 empty] | N/A |  |  |  | 0 |  | 0 |  | 0 |  | 0
IED 52 | CCI 11 |  |  | Audit of current environmental sector plan implementation | N/A | IWMP Audit | Number of current env. sector plans implementation audited | 2 | R0,00 | R0,00 | R0,00 | N/A | Develop audit plan | Audit plan | Consultation process on audit plan | Outcomes report to MANCO on the consultation process | Actual audit - 1st sector plan | Audit pre-liminary report to MANCO | Actual audit - 2nd sector plan | Audit pre-liminary report to MANCO
[9 empty] | n/a | N/A | N/A |  | R0,00 |  | R0,00 |  | R0,00 |  | R0,00
IED 53 | CCI 12 |  | Integrated Coastal Management | Facilitate coastal management stakeholder forum | N/A | 1 forum; 3 meetings/annum | Number of Coastal management stakeholder forum workshops facilitated | 4 | 7360 | 0 | 0 | ES/internal | 1 | Forum minutes; attendance register | 2 | Forum minutes; attendance register | 3 | Forum minutes; attendance register | 4 | Forum minutes; attendance register
[9 empty] | 320150-090-190 | N/A | N/A |  | 2533 |  | 2533 |  | 2533 |  | 2893
IED 54 | CCI 13 |  | Environmental Education and Awareness | Facilitate Invasive Alien Species (IASP)-Forum | all | 1 forum; 4 meetings/workshops | Number of Invasive Alien Species (IASP) stakeholder forum workshops facilitated | 2 | 0 | 0 | 0 | ES/Internal | 1 | Forum minutes; attendance registers | 2 | Forum minutes; attendance registers | N/A | n/a | 1 stakeholder workshop | Forum minutes; attendance registers
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  |  |  | 50000
IED 55 | CCI 13 |  |  | Public Campaigns | All | 5 | Number of External Public campaigns organised | 5 | 184000 | 0 | 0 | ES/Internal | 1 | Campaign programme; e-mail correspondences, attendance register | 2 | Campaign programme; e-mail correspondences, attendance register | 4 | Campaign programme; e-mail correspondences, attendance register | 5 | Campaign programme; e-mail correspondences, attendance register
[9 empty] | 320470-090-190 | N/A | N/A |  | 46000 |  | 92000 |  | 138000 |  | 184000
IED 56 | CCI 13 |  |  | International Environmental days | All | 5 | Number of International Environmental calendar days celebrated | 4 | 0 | 0 | 0 | N/A | 1 | Campaign programme; e-mail correspondences, attendance register | 2 | Campaign programme; e-mail correspondences, attendance register | 3 | Campaign programme; e-mail correspondences, attendance register | 4 | Campaign programme; e-mail correspondences, attendance register
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | 0 |  | 0
IED 57 | CCI 13 |  |  | Eco-/Green office | All | 3 workshops; paper recycling project with Aux Services | Number of Eco-/Green office initiatives (internal education) implemented | 2 | 0 | 0 | 0 | N/A | Evaluation of previous education; Mini-survey of environmental awareness | Survey methodology | Cleaning contractors workshop; Pilot project plan for officials | Outcomes report; attendance register; Pilot plan for officials | Pilot project for officials - Trial | Trial results | 1 | Session material, attendance register
[9 empty] | N/A | N/A | N/A |  | 0 |  | 0 |  | R0,00 |  | 0
IED 58 | CCI 13 |  |  | School Env Education Programme (SEEPRO) | All | 15 SEEPRO Schools | Number of Schools enrolled for SEEPRO | 20 | R0,00 | R0,00 | R0,00 | N/A | Maintain 15 schools membership | List/Database of school, a sample of 5% their env portfolio | n/a | n/a | Workshop and award SEEPRO schools; | Annual Report, attendance register of Award Ceremony/Summit | Enroll and maintain 20 schools membership | List/Database of schools, 5% sample of their env portfolio
[9 empty] | N/A | N/A | N/A |  | R0,00 |  | R0,00 |  |  |  | R0,00
IED 59 | MFVM 5 | Municipal Financial Viability and Management | Supply Chain Management | Vendor Management | NA | New | Percentage compliance with Vendor Management Committee submissions | 100 | N/A | N/A | N/A | N/A | 100% | Report submitted to Vendor Committee | 100% | Report submitted to Vendor Committee | 100% | Report submitted to Vendor Committee | 100% | Report submitted to Vendor Committee
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 60 | MFVM 8 |  | Expenditure Management | Payment of Creditors within 30 days | NA | New | Percentage compliance to submission of invoices within 10 days of receipt of invoice | 100 | N/A | N/A | N/A | N/A | 100% compliance iro submission of invoices | Monthly Departmental control sheet | 100% compliance iro submission of invoices | Monthly Departmental control sheet | 100% compliance iro submission of invoices | Monthly Departmental control sheet | 100% compliance iro submission of invoices | Monthly Departmental control sheet
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 61 | MTID 1 | Municipal Transformation and Institutional Development | Organisational Performance Management System | OPMS Quarterly Reviews | NA | New | Percentage Compliance with submission of performance information | 100 | N/A | N/A | N/A | NA | 100% | Acknowledgement Letter from PMS | 100% | Acknowledgement Letter from PMS | 100% | Acknowledgement Letter from PMS | 100% | Acknowledgement Letter from PMS
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 62 | MTID 1 |  |  | Adoption of Annual Report | NA | New | Percentage Compliance with submission of Annual Report compilation | 100 | N/A | N/A | N/A | NA | 100% | NA | 100% | Acknowledgement of Submission of information from PMS Office | 100% | Acknowledgement of Submission of information from PMS Office | NA | NA
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 63 | MTID 5 |  | Labour Relations | Labour Unrest | NA | New | Number of Management/Union meetings by HOD | 4 | N/A | N/A | N/A | N/A | 1 | Minutes, Attandence Register | 1 | Minutes, Attandence Register | 1 | Minutes, Attandence Register | 1 | Minutes, Attandence Register
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 64 | MTID 5 |  |  |  | NA | New | Number General Staff meetings | 2 | N/A | N/A | N/A | N/A | 0 | Minutes, Attandence Register |  | N/A | 1 | Minutes, Attandence Register | N/A | N/A
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 65 | MTID 5 |  |  |  | NA | New | Number of Departmental meetings | 8 | N/A | N/A | N/A | N/A | 2 | Minutes, Attandence Register | 2 | Minutes, Attandence Register | 2 | Minutes, Attandence Register | 2 | Minutes, Attandence Register
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 66 | MTID 8 |  | Fleet Management | Fleet utilisation | NA | New | Percentage compliance with trip authorisation in respect of fleet utilisation | 100 | N/A | N/A | N/A | N/A | 100% | Summary report of Trip authorisations compliance | 100% | Summary report of Trip authorisations compliance | 100% | Summary report of Trip authorisations compliance | 100% | Summary report of Trip authorisations compliance
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 67 | MTID 16 |  | Legal Compliance | Litigation cases instituted against municipality | NA | New | Percentage compliance with submission of reports on litigious action within 14 days | 100 | N/A | N/A | N/A | N/A | 100% | Proof of submission (Email) | 100% | Proof of submission (Email) | 100% | Proof of submission (Email) | 100% | Proof of submission (Email)
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 68 | MTID 16 |  |  |  | NA | New | Percentage litigation cases instituted against municipality responded to within one week | 100 | N/A | N/A | N/A | N/A | 100% | Proof of submission (Email) | 100% | Proof of submission (Email) | 100% | Proof of submission (Email) | 100% | Proof of submission (Email)
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 69 | GGPP 2 | Good Governance & Public Participation | District Wide Intergovernmental Relations | Functional IGR Structures | NA | New | Percentage compliance by IED on submission of IGR reportst within the required time-frames | 100 | N/A | N/A | N/A | N/A | 100% | Proof of notification and submission (Email) | 100% | Proof of notification and submission (Email) | 100% | Proof of notification and submission (Email) | 100% | Proof of notification and submission (Email)
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
IED 70 | GGPP 8 |  | Internal Auditing | Monitoring Implementation of AG (SA) Management Corrective Action Plan | NA | New | Percentage reduction AG queries | 100 | N/A | N/A | N/A | N/A | 100% | Proof of notification Proof of submission (Email) AND Acknowledgement of receipt of complete information | 100% | Proof of notification Proof of submission (Email) AND Acknowledgement of receipt of complete information | N/A | N/A | N/A | N/A
[9 empty] | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0
END
INDICATORS:
REGULATED : Local Government: Municipal Planning and Performance Management Regulations, 2001
Unique Municipal Department Indicator
Municipal Cross Cutting Indicators
NAME OF OFFICIAL: Zakithi Mbonane | [11 empty] | NAME OF OFFICIAL: Vella Grammoney
SIGNATURE OF OFFICIAL: | [11 empty] | SIGNATURE OF OFFICIAL:
DESIGNATION OF OFFICIAL: General Manager Infrastructure and Ecomic Development | [11 empty] | DESIGNATION OF OFFICIAL: Manager Health Services
DATE: | [11 empty] | DATE:
NAME OF OFFICIAL: Sipho Khuzwayo | [11 empty] | NAME OF OFFICIAL: Mandla Mkhungo
SIGNATURE OF OFFICIAL: | [11 empty] | SIGNATURE OF OFFICIAL:
DESIGNATION OF OFFICIAL: Senior Manager Enviromental Service and Economic Development | [11 empty] | DESIGNATION OF OFFICIAL: Manager LED and Tourism
DATE: | [11 empty] | DATE:
NAME OF OFFICIAL: Noloyiso Wallingo
SIGNATURE OF OFFICIAL:
DESIGNATION OF OFFICIAL: Manager Enviromental Services
DATE: